## Actions
Company | Function | Item | Status | Owner | Founder Dependency | Comments
Aarna | Product | AI Personalization Recommendation Engine | WIP | Kiran | None | In testing phase
Aarna | GTM | Demand-Side B2B Channel Launch | To Start | Nikhil | To Review | Focus on UAE transit tourism
Abhee | Product | Trips Section Design and Interactive Gestures | WIP | Vishwa | None | LiveKit regression complete
Abhee | GTM | UAE Supplier and Creator Partnership Onboarding | Done | Nikhil | None | 2900 experiences added
Miraee | Product | Revenue Generation Engine & Onboarding Flow | To Start | Sailaja | None | Next 15 days sprint

## Decisions
Decision | Owner | Status | Founder Dependency | Impact if delayed | Deadline
UAE GTM Expansion Execution Plan | Nikhil | WIP | To Review | Loss of 1st mover market penetration | 2026-09-15
AI LLM Routing & Cost Optimization Strategy | Hemanth | To Start | To Review | Higher API inference costs | 2026-09-10
Creatorpreneur Monetization Model | Kiran | To Start | Decision | Delay in supply network rollout | 2026-09-20

## Priorities
Priority | Group | Focus Area | Why | Horizon
1.0 | Pranik Products | P4P / P4D / P4H Integration | Product readiness for rapid GTM rollout | Next 15 days
2.0 | Pranik GTM | Indian Army & SPV Partnerships | Data source for SLMs and market leadership | Next 30 days
3.0 | Aarna Product | Digital Stores & Whitelight Platform | Core feature set readiness for creators | Next 30 days

## Pranik
Function | Item | Status | Owner | Founder Dependency | Comments
Product | CDSS and Scribe Auto-Doctor Assignment | Done | Praveen | None | Deployed in pilot clinic
Product | Cancer Constant Care Support Module | On Hold | Natesh | Decision | Reviewing Phase-1 priority
GTM | Kiosk White-Label Hardware Evaluation | Done | Karthik | None | Hardware specs finalized